## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
List User Story steps that were not completed at Sprint End

## Sprint Backlog 1
| User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | USBookCSMT:001 | 1 | Class Design | Siddhant | 13/7/2020 | 4 hr | 2 hrs | Completed | 1 hr
|  | 2 | Interface Design | Siddhant | 13/7/2020 | 4 hr | 2 hrs | Completed | 1 hr
2 | USBookCSMT:002 | 1 | Test plan | Siddhant | 14/7/2020 | 2 hr | 1 hr | Completed | 1 hr
3 | USBookCSMT:003 | 1 | Creating a Spring boot starter Project | Siddhant | 14/7/2020 | 2 hr | 1 hr
4 | USBookCSMT:004 | 1 | Entity Class Design of shipping and table created | Siddhant | 2020-07-15 | 3hr | 2hr | completed | 1 hr
5 | USBookCSMT:005 | 1 | DAO implementation of shipping | Siddhant | 2020-07-15 | 3 hr | 2hr | completed | 1 hr
|  | 2 | DAO implementation of payment | Siddhant | 2020-07-15 | 2 hr | 1 hr | completed | 1 hr
6 | USBookCSMT:006 | 1 | Service implementation shipping | Siddhant | 2020-07-15 | 2 hr | 1 hr | completed | 1 hr
|  | 2 | Service implementation payment | Siddhant | 07/15/2020 | 2 hr | 1 hr | completed | 1 hr
7 | USBookCSMT:007 | 1 | Controller implemetation of Shipping details | siddhant | 07/15/2020 | 4 hr | 2 hr | completed | 1 hr